## Sheet1
Project Plan for Model A.1
Business Case ID:
Proposed title
Key operational deliverable dates completed by the centre: |  |  | Required Date
Window of Opportunity: (date qualification to be operationalised by)
Group Award Validation by: Note: venue should be booked and SQA officer invited ie. QM qualification will belong to
Support Materials published by (if applicable):
Final qualification structure and Unit writer briefs by:
Units submitted to SQA by: (QPM will identify and agree participation of a peer reviewier if applicable) The SQA Lead Officer will identify dates for Unit writer training sessions and provisionally book places for writers
Key operational deliverable dates completed by the SQA Lead Officer: |  |  | Required Date
Provisionally book places on Unit writer training sessions
Draft Web Product Overview by:
Qualification Partnership Agreement / Joint Certificate development process completed by (if applicable) Note: a member of the Regulated Qualifications section of QPM should be contacted asap to assist with setting up the QPA / joint certificate.
Verifier requirements confirmed ie existing group / re-alloction of existing verifiers / new group to be set up on APS - recruitment required. (Where recruitment required, Appointee Management must be informed ASAP as External Verifiers need to carry out qualification appoval. Where a new group is to be created on APS, Qualification Approval must be notified asap. Any specific approval requirements have been identified and recorded)
Develop - establishing content and structure (maximum time line of 10 weeks) | Responsibility of | Baseline Date | Estimated number of days for task
Establish a Qualification Design Team (QDT) | Lead Officer - Centre
Identify dates, time and venue | Lead Officer - Centre
Identify and recruit QDT members | Lead Officer - Centre
First meeting of QDT
Produce proposed qualification structure and Unit overviews | QDT
Agree consultation strategy | QDT
Authorise payment of QDT expenses | Lead Officer - Centre
Carry out agreed consultation | Lead Officer - Centre
Conclude consultation | Lead Officer - Centre
Collate consultation data and analyse findings | Lead Officer - Centre
Second meeting of QDT
Review and evaluate consultation responses | QDT
Finalise qualification structure, copy to QPM (see key dates above) | QDT
Draft Unit writer briefs for each new/revised Unit | QDT
Authorise payment of QDT expenses | Lead Officer - Centre
Third meeting of QDT
Finalise Unit writer briefs for each new/revised Unit, copy to QPM (see key dates above) | Lead Officer - Centre
Identify writers and vetters for the Units and Assessment Support Packs | QDT
Identify writer for the Group Award specification | QDT
Identify validation panel members | QDT
Identify membership of Qualification Support Team (if applicable) | QDT
Conclude QDT | Lead Officer - Centre
Authorise payment of QDT expenses | Lead Officer - Centre
Develop - Units (maximum time line of 8 weeks) | Responsibility of | Baseline Date | Estimated number of days for task
Contract Unit and Group Award specification writers | Lead Officer - Centre
Recruit validation panel members | Lead Officer - Centre
Contact Regulated Qualification Section of QPM to discuss Qualification Partnership Agreement / Joint Certification (if applicable) | Lead Officer - SQA
Unit writer training session (see key dates above) | OD/writing trainers
Units submitted to SQA (see key dates above) | Writers
Technical Edit of Units | Lead Officer - SQA
Peer review of Units (if applicable) | As assigned by QPM
Send Units to Subject Specialist (vetter) | Lead Officer - SQA
Submit a Core Skills claim (if applicable) | Lead Officer - SQA
Vetted Units received and amended as appropriate | Lead Officer - SQA
Units validated | Lead Officer - SQA
Validated Units sent to person leading the development and Document Processing | Lead Officer - SQA
Completed Checklist 3 - subject specialist check and Unit Reference template e-mailed to QPM | Lead Officer - SQA
Validated Units sent to Group Award specification writer | Lead Officer - Centre
Develop - Group Award (maximum time line of 10 weeks) | Responsibility of | Baseline Date | Estimated number of days for task
Draft Group Award specification submitted to Lead centre | Writer
Group Award specification technically edited and amended as appropriate | Lead Officer - Centre
Send validation materials to panel members (2 weeks before meeting) | Lead Officer - Centre
Group Award Validation meeting
Authorise payment of validation panel members expenses | Lead Officer - Centre
Revise Group Award specification (if applicable) | Writer/Lead Officer -centre
Group Award Validated
Send signed validation report to SQA | Lead Officer - Centre
Send completed DAVAL 1, Group Award specification and Graded Units (if applicable) to SQA | Lead Officer - Centre
Authorise payment of Group Award specification writer | Lead Officer - Centre
Operationalise (maximum time line of 2 weeks) | Responsibility of | Baseline Date | Estimated number of days for task
Confirm all operational deliverables are in place with QPM to ensure DPG sign off | QPM
E-mail completed DAVAL 1 to Reference Section for inputing on APS | QPM