QPM  monitors development progress and reports to DPG

QPM  monitors development progress and reports to DPG

QDT first set of deliverables – the QDT will produce a:

- proposed qualification structure and Unit overviews for each new/revised Unit

- consultation strategy

Centre produces consultation documentation and implements agreed consultation strategy to confirm suitability of proposed qualification structure

Note: the SQA Lead Officer should be sent details of the proposed qualification structure to check there is no overlap with existing provision

QDT second set of deliverables – the QDT will produce:

- an evaluation of stakeholder responses

- a final qualification structure

- draft Unit writer briefs for each new/revised Unit

Centre:

- finalises the qualification structure and e-mails it to QPM along with copies of Unit writer briefs for each new/revised Unit

- updates the Group Award specification

- proceeds to phase 2 – developing the product

SQA Lead Officer produces a draft Web Product Overview Sheet (with assistance from the centre if needed) and e-mails it to QPM.

QDT third deliverable – the QDT will:

- finalise Unit writer briefs

- identify  writers and vetters for:

- Units/ASPs

- Group Award specification

- Identify possible validation panel members

Gateway 2 – SQA approve centre’s  proposal to develop a qualification

SQA Lead Officer provides centre with a partially completed Group Award specification using relevant information from the Business Case

Centre:

- completes as much of the project plan as possible and e-mails it to SQA’s Qualification Portfolio Management Team (QPM) QPMTeam@sqa.org.uk

- establishes Qualification Design Team (QDT)

QPM update the Centralised Development Schedule (CDS) with the key and baseline dates stated on the project plan

QPM:

- Updates the CDS and Unit Development Register

- e-mails Lead Officer details of number of Units that are to be peer reviewed and the name of peer reviewer (if applicable)

- Saves draft Web Product Overview Sheet in the Business Case folder and e-mails link to Marketing

Marketing use information from the Web Product Overview Sheet to begin process of setting up a subject page on SQA’s website once qualification is coded on APS