## Sheet1
Project Plan for Centre Led Group Award Development and Validation
Proposed title
Key operational deliverable dates completed by the centre: |  | Required Date
Submit a Development Opportunity Form to SQA to inform them of development intentions by:
Date Group Award to be coded on APS by:
Group Award Validation date: Note: venue should be booked and SQA officer invited (SQA Qualification Manager whose portfolio the Group Award will be part of
Units submitted to SQA for validation by: (if applicable) Note: the technical edit and subject specialist checklists and Equality Review form must also be submitted
Submission of assessment exemplification to SQA for prior verification by: (if applicable)
Draft Web Product Overview submitted to SQA by:
QDT meetings (dates identified and venue booked) by:
Unit writer training on SQA Academy to be completed by:
Equality Review Training on SQA Academy to be completed by:
Units written and vetted by: (if applicable)
Units submitted to SQA by - include technical edit and subject specialist checklists and Equality Review form :
Date of Core Skill audit and validation meeting
Group Award Specification written by:
End of Project by: (DAVAL1 Form, signed validation report, validated Group Award Specification, Graded units (if applicable) and completed Web Product Overview submitted to SQA).
Key operational deliverable dates completed by the SQA Lead Officer: |  | Required Date
Verifier requirements confirmed ie existing group / re-alloction of existing verifiers / new group to be set up on APS - recruitment required. (Where recruitment required, Appointee Management must be informed ASAP as External Verifiers need to carry out qualification appoval. Where a new group is to be created on APS, Qualification Approval must be notified asap. Any specific approval requirements have been identified and recorded)
Develop - establishing content and structure | Responsibility of | Baseline Date
Establish a Qualification Design Team (QDT) | Lead Officer - Centre
Identify dates, time and venue | Lead Officer - Centre
Identify and recruit QDT members | Lead Officer - Centre
First meeting of QDT
Produce proposed qualification structure and unit overviews | QDT
Agree consultation strategy | QDT
Carry out agreed consultation | Lead Officer - Centre
Conclude consultation | Lead Officer - Centre
Collate consultation data and analyse findings | Lead Officer - Centre
Second meeting of QDT
Review and evaluate consultation responses | QDT
Finalise qualification structure | QDT
Draft unit writer briefs for each new/revised unit (if applicable) | QDT
Third meeting of QDT
Finalise unit writer briefs for each new/revised | Lead Officer - Centre
Identify and recruit writers and vetters for the units | QDT
Identify and recruit writer for the Group Award specification | QDT
Identify possible validation panel members | QDT
Book validation meeting venue | Lead Officer - Centre
Conclude QDT | Lead Officer - Centre
Produce a draft Web Product Overview and e-mail it to the SQA Lead Officer (see key dates) | Lead Officer - Centre
Develop - units (including graded units if applicable) | Responsibility of | Baseline Date
Contract Unit and Group Award specification writers | Lead Officer - Centre
Confirm composition of the validation panel | Lead Officer - Centre
Technical Edit of units | Lead Officer - Centre
Subject Specialist (vetter) review of units | Lead Officer - Centre
Carry out Equality Review | Lead Officer - Centre
Units submitted to SQA (see key dates) | Lead Officer - Centre
SQA reviews documentation and informs centre of any necessary changes | Lead Officer - SQA
Units validated (except graded units) | Lead Officer - SQA
Submit units to SQA Document Processing for housestyling and finalisation | Lead Officer - SQA
Complete a unit Coding form and e-mail to QPM | Lead Officer - SQA
Units reviewed for embedded Core Skills and audited as appropriate | QPM - SQA
Develop - Group Award | Responsibility of | Baseline Date
Group Award specification produced | Writer
Group Award specification technically edited and amended as appropriate | Lead Officer - Centre
Validate | Responsibility of | Baseline Date
Send validation materials to panel members (2 weeks before meeting) | Lead Officer - Centre
Group Award Validation meeting (see key dates)
Authorise payment of validation panel members expenses | Lead Officer - Centre
Revise Group Award specification (if applicable) | Writer/Lead Officer -centre
Group Award Validated (and graded units if applicable)
E-mail signed validation report to SQA | Lead Officer - Centre
Operationalise | Responsibility of | Baseline Date
E-mail completed DAVAL 1, Group Award specification, Graded Units (if applicable) and Web Product Overview to SQA | Lead Officer - Centre
Create Group Award structure on APS | Reference
Complete form for inclusion in SQA’s weekly centre news. | Lead Officer
Publication of Group Award Specification on qualification page on SQA website | Digital Team
Units uploaded to unit search facility on SQA website | QPM - SQA
Add to relevant catalogue | QPM - SQA
Add to relevant annual report | QPM - SQA
Template: October 2019